## Slide 1: Cut MARG’s cloud bill by 15–20% in 90 days
MANAGEMENT BRIEFING
A 90-day action plan for Azure and WebberStop, then a monthly cycle that keeps the savings coming.
Prepared for MARG management · 20 October 2026 · Based on April–September 2026 bills and server monitoring
Notes: Opening: the cloud bill is ₹68.1 L a month and rising. This plan targets 15–20% savings within 90 days, and is explicit about how firm each number is.

## Slide 2: ₹68.1 L a month today; up to ₹14.7 L* can be saved
THE SITUATION
SPEND TODAY
₹68.1 L
a month in September, up 9% since April
MANAGEMENT GOAL
15–20%
₹10.2 L to ₹13.6 L a month, within 90 days
PLAN CEILING
₹14.7 L*
a month by day 90, or 22% of spend, if every owner says yes
We need owners’ decisions for validating and confirming analysis, so we ask for answers within 14 days.
MARG cloud cost plan · 90 days
2
* This does not include cost savings from MARG ERP Live Order Database Migration to WebberStop which will be approx. additional ~ ₹ 15.0 L per month.
Notes: September spend was ₹68.11 L: Azure ₹29.81 L and WebberStop ₹38.30 L. The goal is 15–20% (₹10.2 L to ₹13.6 L). The plan ceiling is up to ₹14.7 L, 22% of spend, but only ₹24.8K is proven by bills and measured load today. Everything else needs an owner to say yes.

## Slide 3: Spend is up 9% since April, driven by WebberStop
WHERE THE MONEY GOES
Spend per month, ₹ lakh. WebberStop +24%, Azure −5% since April
Azure (net)
WebberStop servers
WebberStop shared
62.4
Apr
60.9
May
54.4
Jun
60.4
Jul
64.5
Aug
68.1
Sep
64%
of WebberStop’s ₹7.4 L rise is Kubernetes plus GPU
₹2.66 L
Kubernetes in September, from ₹1.9K in June
₹2.12 L
GPU servers in September, from ₹67.5K
The run-rate is higher than the bill: at closing size WebberStop is about ₹41.2 L a month, not ₹38.3 L.
MARG cloud cost plan · 90 days
3
Notes: Total spend moved from ₹62.4 L in April to ₹68.1 L in September, up 9%. WebberStop rose 24% while Azure fell 5%. Kubernetes usage went from ₹1.9K in June to ₹2.66 L in September, and GPU servers from ₹67.5K to ₹2.12 L; together they are 64% of the ₹7.4 L WebberStop increase. The September bill understates the run-rate because servers were added during the month.

## Slide 4: Servers use only 8% of the CPU we pay for
WHY THE BILL IS HIGH
Average CPU in use across 134 monitored WebberStop servers
8%
of the vCPU we pay for, and only 21% in busy hours
Average CPU in use by product line, October to 20 Oct
Azure VMs
17.8%
BOOKS
8.2%
CLOUD
7.2%
ERP
2.1%
The other side: 19 servers run hot and need more capacity. We fix these first, then shrink the idle ones.
MARG cloud cost plan · 90 days
4
Notes: On 134 monitored WebberStop servers, average CPU in use is 8% of the vCPU paid for, and 21% in busy hours. Averages hide spikes, so only servers that also pass a spike test are proposed for a smaller size. 36 servers peaked below 15% CPU even in their busiest hours; 59 servers hold large disks that never passed half full. 19 other servers are the opposite: 12 have disks 99% full or more, and the audit logged 5,627 alerts on them in 30 days.

## Slide 5: Every saving is labelled by how firm it is
CONFIDENCE
PROVEN
₹24.8K
Bills and 30 days of server load: 12 right-sizing moves and 22 unused IPs.
Counts as saved
TO CONFIRM
up to ₹7.7 L
Real, but an owner must say yes: old Azure servers, silent servers, discount, disks.
Counts once confirmed
ESTIMATE OR TARGET
up to ₹7.2 L*
Rests on an assumed price or percentage: Azure tuning, first moves, Kubernetes curb.
Not counted as saved
We report the three buckets separately every week. Lines overlap slightly, so they are not added together.
MARG cloud cost plan · 90 days
5
* This does not include cost savings from MARG ERP Live Order Database Migration to WebberStop.
Notes: Proven means backed by the bills or 30 days of hourly server load. To confirm means real but needing an owner’s yes; it is a ceiling that covers the old Azure side, silent and idle servers, the missing discount, disks and further right-sizing. Estimate or target rests on an assumed price or percentage: Azure and backup tuning, the first moves to WebberStop and curbing Kubernetes growth. Only the first two count as saved. Azure figures are net of an assumed 15% partner discount, and the ₹2.64 L Kubernetes growth is not in the ceiling.

## Slide 6: Eight actions carry most of the saving
THE PLAN ON A PAGE
Maximum saving per month, ₹ lakh
Owner confirms
Estimate or target
Move six workloads to WebberStop
₹3.26 L
Reserve and trim Azure and backup
₹2.95 L
Switch off almost-unused servers
₹2.34 L
Stop the old Azure side of moved servers
₹2.01 L
Curb Kubernetes growth (half, as target)
₹1.32 L
Confirm and stop nine silent servers
₹1.26 L
Claim the missing 40% WebberStop discount
₹0.89 L
MARG cloud cost plan · 90 days
6
Live Order Database Migration to Webber
~₹15.0 L
Notes: The seven largest actions by monthly saving. Moving workloads (₹3.26 L) and reserving and trimming Azure (₹2.95 L) are estimates. Switching off idle servers (₹2.34 L), stopping the old Azure side of moved servers (₹2.01 L), silent servers (₹1.26 L) and the missing 40% discount (₹89.3K) need an owner to confirm. The Kubernetes figure is half of the ₹2.64 L growth, a target rather than evidence. Actions overlap slightly, so the bars are not added together.

## Slide 7: The 90-day target is up to ₹14.7 L a month*
THE 90-DAY TARGET
Cumulative saving, ₹ lakh a month
4.29
10.85
13.37
14.70
Goal 15%: ₹10.2 L
Goal 20%: ₹13.6 L
Step 1, day 30
Step 2, day 90
+ First 3 moves, estimate
+ Kubernetes curb, target
₹10.9 L
from Steps 1 and 2 alone, 16% of spend
70%
of the ceiling must land to reach 15%, so decisions are needed in weeks
MARG cloud cost plan · 90 days
7
* This does not include cost savings from MARG ERP Live Order Database Migration to WebberStop.
Notes: Cumulative saving: Step 1 gives up to ₹4.29 L by day 30, Step 2 takes it to ₹10.85 L by day 90 (16%), the first three moves to WebberStop add ₹2.52 L (estimate) and a Kubernetes curb adds about ₹1.3 L (target), reaching ₹14.7 L or 22%. The goal band is 15% (₹10.2 L) to 20% (₹13.6 L). Evidence mix of the ceiling: ₹24.8K proven, ₹7.7 L needs owners to say yes, ₹6.8 L rests on assumed percentages or targets. To reach 15%, about 70% of the ceiling has to land.

## Slide 8: Quick wins first, then size, then move
ROADMAP
Day 0
Day 30
Day 60
Day 90
Month 6
Step 1 · Quick wins
up to ₹4.3 L a month
Step 2 · Size and tune
up to ₹6.6 L a month
Step 3 · Move
up to ₹3.3 L a month and MARG ERP migration, est. (₹15.0 L a month approx.)
Step 4 · Keep improving
up to ₹0.4 L a month
Quick wins
Switch off, resize, tune
First 3 moves by day 90, the rest by month 6
Monthly re-run, ongoing
Day-90 checkpoint: up to ₹14.7 L a month if every owner has said yes and additional MARG ERP migration at ₹15.0 L a month
MARG cloud cost plan · 90 days
8
Notes: Step 1 (days 0–30): silent servers, the old Azure side, the discount claim, capacity fixes, monitoring and the Kubernetes breakdown. Step 2 (days 30–90): switch off, right-size, shrink disks, reserve and trim. Step 3 (day 60 to month 6): the first three workloads move by day 90, the rest by month 6. Step 4 is a monthly re-run. Days count from approval of the plan.

## Slide 9: Quick wins and urgent fixes: up to ₹4.3 L a month
STEP 1 · DAYS 0–30
What to do | Saving a month | Risk
Stop the old Azure side of 4 moved servers | up to ₹2.01 L | Medium
Confirm 9 silent servers, then stop paying | up to ₹1.26 L | Medium
Ask WebberStop for the missing 40% discount | up to ₹89.3K | Low
Release 22 unused IPs and retired-server charges | up to ₹12.4K | Low
Fix 19 servers short of CPU, memory or disk | Spend to add | High
Monitor 70 billed servers nobody measures | Enables ₹9.15 L | Low
Explain Kubernetes growth, curb idle workloads | ₹2.64 L to explain | Medium
MARG cloud cost plan · 90 days
9
Notes: Step total is approximately ₹4.29 L a month; lines overlap slightly. The capacity fixes come first so that resizing elsewhere never puts a stressed server at risk: 12 of the 19 servers have a disk 99% full or more. The 70 unmeasured servers cost ₹9.15 L a month, about a quarter of the bill, and include the new ProdSQL server and both GPU servers. The old Azure side of ProdSQL is 95% of the ₹2.01 L figure. Two of the 40% discount lines are GPU servers (₹84.8K of the ₹89.3K). Only ₹3.4K of the ₹12.4K clean-up is proven by the bill.

## Slide 10: Switch off, right-size and tune: up to ₹6.6 L a month
STEP 2 · DAYS 30–90
What to do | Saving a month | Risk
Switch off 36 idle servers, review 2 GPU servers | up to ₹2.34 L | Medium
Right-size 30 servers with spare capacity | up to ₹53.7K | Medium
Shrink over-provisioned disks on 59 servers | up to ₹73.8K | Medium
Reserve and trim 45 Azure resources | up to ₹2.95 L | Medium
Proven today: ₹21.3K of the right-sizing is backed by measured load. 13 more servers need a price or DBA check.
With Step 1, this reaches ₹10.9 L a month, 16% of spend, by day 90.
MARG cloud cost plan · 90 days
10
Notes: Step total is approximately ₹6.56 L a month. The 36 idle servers peaked below 15% CPU even in their busiest hours and averaged under 5% for 30 days. Owners answer by day 40; we snapshot and stop, then delete after two weeks. GPU load is not measured, so the two GPU servers cannot be judged yet. Right-sizing starts in week 5 with the 12 proven servers, one per maintenance window. Reservations are bought only for servers that stay, once the move list is firm at day 60. The 10–25% trim percentages are assumptions, so the ₹2.95 L is an estimate until owners review the biggest resources.

## Slide 11: Moving six workloads to WebberStop saves up to ₹3.26 L
STEP 3 · DAY 60 TO MONTH 6
Same sizes at WebberStop’s current prices
₹3.26 L
a month, an estimate: Azure ₹4.61 L falls to about ₹1.35 L
Data transfer and licence differences are not counted, so the real saving is likely higher.
Workload | Saving a month | Lands by
VM-App2 | ₹1.49 L | Day 90
VM-ReportServer | ₹57.6K | Day 90
VM-APP2NSYNC | ₹45.5K | Day 90
VM-APP2-New | ₹38.6K | Month 6
ECOD | ₹27.3K | Month 6
WhatsApp | ₹7.7K | Month 6
The first three, worth ₹2.52 L, land by day 90.
MARG cloud cost plan · 90 days
11
Notes: Six Azure workloads cost ₹4.61 L a month for servers, disks and network items; the same sizes at WebberStop’s current prices are about ₹1.35 L. WebberStop has no ingress or egress charges and cheaper Windows and SQL Server licences than Azure, which are not counted here. Quote and compliance review start in days 0–30, the pilot lands by day 60 and the first three workloads (₹2.52 L) by day 90. Legal and security must confirm the data may sit with WebberStop, Windows and SQL Server licence terms must allow the move, and the pilot measures latency to users and databases.

## Slide 12: Three checks must clear before more workloads move
STEP 3 · BEFORE MORE MOVES
COMPLIANCE FIRST
₹7.5K
a month at stake, 1 workload
Health data (ABHA) moves only after Legal and Security approve.
Legal + Security · High risk
RE-PLATFORM FIRST
₹1.84 L
a month on Azure SQL and App Service, 7 workloads
Rebuild as servers with SQL licences first. Largest is MargBooks-VM, ₹1.27 L.
App owners + DBA · Medium risk
SERVER SIZES FIRST
₹7.18 L
a month on Azure, 7 workloads not in Zabbix
Sizes are unknown, so they cannot be priced. Largest is VM-MargME9, ₹2.98 L.
DevOps · Low risk
MARG cloud cost plan · 90 days
12
Notes: ABHA looks cheaper at WebberStop, but only if Legal and Security approve data location, certifications and customer contracts; the review starts in week 1. Azure SQL and App Service cannot be copied to WebberStop as they are; get a quote in Step 1. Seven Azure servers are not in Zabbix, so their size is unknown; install the agent or list the sizes in Step 1.

## Slide 13: Every action has a check and a way back
SAFEGUARDS
Stop, then delete
Servers are snapshotted and stopped, then kept for two weeks before removal.
Fix before shrinking
The 19 servers short of capacity are fixed first and are never shrunk.
One change at a time
Resizing runs one server per maintenance window, with the DBA checking databases.
Proof before credit
A saving counts only with a bill, measured load or a written answer from the owner.
MARG cloud cost plan · 90 days
13
Notes: Each action in the plan carries a verify-before-acting list. Common rules: check the backup is restorable and nothing still connects before stopping a server; match old and new sides by workload, not just name; check month-end peaks fall inside the 30-day window before resizing; confirm licence terms for core-based software; and get WebberStop’s discount answer in writing before claiming the saving. The high-risk items are the capacity fixes and the compliance review.

## Slide 14: Six owners confirm the actions, each with a date
ACCOUNTABILITY
Owner | Confirms | By when
Infra lead | Old Azure side of 4 servers (₹2.01 L) | Day 30
Procurement | WebberStop discount (₹89.3K) and move quote | Day 30
DevOps, app owners | Silent servers, capacity fixes, idle servers | Day 30 and 90
DBA | Database resizing and re-platforming | Days 30–90
Legal + Security | Data location and contracts, ABHA first | Day 45
Cloud lead | Reservations, trims, first 3 moves (₹2.52 L) | Day 90
Owners are the roles named in the plan. Days count from approval of this plan.
MARG cloud cost plan · 90 days
14
Notes: Infra lead: old Azure side of four servers, backups of retired servers and backup retention (retention by day 90). Procurement: the missing 40% discount, whether stopped test servers bill less, and the WebberStop quote for the moves. DevOps with app owners: silent servers, IPs, capacity fixes, monitoring and the Kubernetes breakdown by day 30; idle servers, right-sizing and disks by day 90. DBA: SQL memory cap, database right-sizing and hot database servers, with re-platforming by month 6. Legal and Security: review starts in week 1 and clears by day 45. Cloud lead: reservations, trims and the first three moves by day 90, remaining moves by month 6, then monthly tuning.

## Slide 15: A monthly cycle keeps the savings coming
STEP 4 · ONGOING
1
Re-run monthly
Fresh server data and bills re-price the list and catch new idle or silent servers.
2
Report in three buckets
Proven, confirmed and assumed savings, shown separately against the 15–20% goal.
3
Set next month’s list
Owners get a short list of decisions, largest saving first, each with a due date.
Also in Step 4: tuning the remaining Azure services adds up to ₹44.3K a month.
MARG cloud cost plan · 90 days
15
Notes: After the big moves, the remaining Azure services (Azure SQL, NAT gateways, application gateways, Log Analytics, public IPs, VPN gateways) add up to ₹44.3K a month at an assumed 15%. More valuable is the cycle itself: every month, new Zabbix data decides the next switch-off, resize or move. Only proven and owner-confirmed savings count as saved.

## Slide 16: What we need from management this week
DECISIONS NEEDED
1
Mandate owners to answer within 14 days
Up to ₹7.7 L a month depends on their yes or no.
2
Authorise two requests to WebberStop
The missing 40% discount, and a quote for six workloads (₹3.26 L estimate).
3
Start the legal and security review now
Data location and contracts come before any move. ABHA is first.
4
Set aside budget for capacity fixes
19 servers are short of capacity. DevOps and DBA size the amount in week 1.
5
Review progress at day 30 and day 90
Proven, confirmed and assumed savings, against ₹10.2 L to ₹13.6 L a month.
MARG cloud cost plan · 90 days
16
6
Decide on urgent basis the live order database migration for MARG ERP to Webber.
Confirmed and assumed savings, around ₹15.0 L a month at a minimum.
Notes: Close with the five asks. Proven today is ₹24.8K a month; up to ₹7.7 L more depends on owners’ answers within 14 days. Authorise the discount request and the quote for the six workloads that could move, with the first three by day 90. Start the legal and security review now. Ask DevOps and DBA to size the capacity-fix budget in week 1. Review progress at day 30 and day 90 against the 15–20% goal.