## Slide 1
MARG cloud cost management plan
A 90-day plan to cut 15–20% of monthly cloud spend, then keep improving
Azure and WebberStop review, April–September 2026
₹68.11 L
cloud spend a month (Sep 26)
up to ₹14.7 L
a month by day 90 if owners confirm (22% of spend)
₹24.8K
a month proven today by bills and measured load
Prepared for MARG management · 20 October 2026
Notes: Azure is net of an assumed 15% partner discount. The day-90 figure is a ceiling that assumes every owner says yes and every estimate holds; actions overlap slightly, so it is an upper bound. Only the proven part counts as saved.

## Slide 2: Cloud spend is ₹68.1 L a month, up 9% since April
SEP 26 SPEND
₹68.11 L
Azure ₹29.81 L · WebberStop ₹38.30 L
Your move: See where it grew on the next slide.
PROVEN SAVING
₹24.8K
a month, backed by bills and measured load
Your move: Do the proven Step 1 and 2 actions.
TO CONFIRM WITH OWNERS
up to ₹7.7 L
a month; a ceiling, an owner must say yes
Your move: Send the Step 1 and 2 checks to the owners.
AZURE → WEBBERSTOP
₹3.26 L
a month estimate, 6 workloads; 7 more need server sizes
Your move: Request a quote now; first 3 moves by day 90.
SHORT OF CAPACITY
19 servers
running hot on CPU, memory or disk
Your move: Fix these in Step 1, before shrinking anything.
Reading these numbers
Azure is net of an assumed 15% partner discount. Lines overlap slightly, so do not add them blindly. The Kubernetes growth (₹2.64 L) is not counted: it first needs explaining.
Notes: The app's earlier 'to confirm' tile included the Kubernetes growth (₹2.64 L), which is a cost to explain rather than a saving. The app now excludes it, so tile and deck agree at ₹7.65 L.

## Slide 3: WebberStop drives the rise, led by Kubernetes and GPU charges
Spend per month, ₹ lakh (total in brackets)
Chart: 
| Apr (62.4) | May (60.9) | Jun (54.4) | Jul (60.4) | Aug (64.5) | Sep (68.1)
Azure (net) | 31.54 | 29.59 | 24.49 | 26.86 | 29.47 | 29.81
WebberStop servers | 25.16 | 25.7 | 24.74 | 25.88 | 26.59 | 29.58
WebberStop shared (backup, Kubernetes, firewall) | 5.7 | 5.56 | 5.17 | 7.61 | 8.41 | 8.72
Total ₹62.4 L (Apr) to ₹68.1 L (Sep): +9%. WebberStop +24%, Azure −5%.
Kubernetes usage went from ₹1.9K (Jun) to ₹2.66 L (Sep). GPU servers went from ₹67.5K to ₹2.12 L.
Together they are 64% of the ₹7.4 L WebberStop increase since April.
The Sep bill understates the run-rate: at closing size WebberStop is about ₹41.2 L a month, not ₹38.3 L.
Notes: Azure is net of an assumed 15% partner discount. Kubernetes and GPU were nil in April and May.

## Slide 4: Paid capacity is mostly idle: servers use 8% of billed vCPU
Average CPU use by product line, % (servers monitored every month)
Chart: 
| May | Jun | Jul | Aug | Sep | Oct*
Azure VMs | 14.8 | 16.2 | 15.6 | 16.1 | 17.5 | 17.8
BOOKS | 6 | 6.3 | 7.1 | 5.7 | 7 | 8.2
CLOUD | 6.1 | 6.5 | 6.9 | 6.6 | 7.8 | 7.2
ERP | 1.2 | 1.2 | 1.3 | 1.9 | 1.9 | 2.1
* October is partial (to 20 Oct)
On 134 monitored WebberStop servers, average CPU in use is 8% of the vCPU paid for, and 21% in busy hours.
Averages hide spikes, so only servers that also pass a spike test are proposed for a smaller size.
19 other servers are the opposite: they run hot and need headroom (Step 1).
Notes: Source: Zabbix hourly CPU readings, 2026-04-01 to 2026-10-20, 179 monitored hosts.

## Slide 5: How firm each number is
PROVEN
₹24.8K a month
Proven by the bills or 30 days of hourly server load. Today: 12 right-sizing moves and 22 unused public IPs.
TO CONFIRM
up to ₹7.7 L a month
Real, but an owner must say yes first. A ceiling: old Azure side, silent and idle servers, missing discount, disks, further right-sizing.
ESTIMATE OR TARGET
up to ₹7.2 L
Rests on a price or percentage we assumed: Azure and backup tuning, the first moves to WebberStop, curbing Kubernetes growth.
Report it in three buckets. Track proven, confirmed by owners and assumed separately every week; only the first two count as saved. Lines overlap slightly, and the ₹2.64 L Kubernetes growth is not in the ceiling. Azure is net of an assumed 15% partner discount.

## Slide 6: The 90-day target: up to ₹14.7 L a month, 22% of spend
Cumulative saving, ₹ lakh a month (goal: 10.2 to 13.6)
Chart: 
| Step 1 · day 30 | Step 2 · day 90 | + First 3 moves | + Kubernetes curb
Cumulative saving | 4.29 | 10.85 | 13.37 | 14.7
Goal: 15% is ₹10.2 L, 20% is ₹13.6 L a month.
Steps 1–2 alone are ₹10.9 L (16%). The first 3 moves and a Kubernetes curb take it to ₹14.7 L.
Evidence mix: ₹24.8K proven, ₹7.7 L needs owners to say yes, ₹6.8 L rests on assumed percentages or targets.
To reach 15% about 70% of the ceiling must land, so decisions are needed in weeks, not months.
Notes: Day-90 ceiling = Step 1 (₹4.29 L) + Step 2 (₹6.56 L) + first moves (₹2.52 L: VM-App2, VM-ReportServer, VM-APP2NSYNC) + half the Kubernetes growth (₹1.32 L). Reservations exclude Azure servers that retire or move. Treat as an upper bound.

## Slide 7: The roadmap: quick wins first, then size, then move
Day 0
30
60
90
180
Step 1 · quick wins
up to ₹4.3 L a month
Silent, old Azure side, discount
Step 2 · switch off, size, tune
up to ₹6.6 L a month
Idle, right-size, disks, reservations
Step 3 · move to WebberStop
up to ₹3.3 L est. a month
First 3 by day 90
Step 4 · keep improving
up to +₹0.4 L a month
Monthly re-run
Day-90 checkpoint: up to ₹14.7 L a month if every owner has said yes

## Slide 8: Step 1 · Quick wins and urgent fixes
Step total: up to ₹4.29 L a month
1
DAYS 0–30
Confirm and clean up what is clearly wasted, fix what is short of capacity, and start the measurements and quotes that Steps 2 and 3 depend on.
What to do | Applies to | Approx. saving /mo | Proven /mo | Risk
Switch off the old Azure side of moved servers | 4 pairs | up to ₹2.01 L | – | Medium
Confirm silent servers, then stop paying for them | 9 servers | up to ₹1.26 L | – | Medium
Ask WebberStop for the missing 40% discount | 4 servers | up to ₹89.3K | – | Low
Release unused IPs and charges for retired servers | 23 lines | up to ₹12.4K | ₹3.4K | Low
Fix servers short of CPU, memory or disk | 19 servers | spend to add | – | High
Put monitoring on unmeasured billed servers | 70 servers | enables ₹9.15 L | – | Low
Explain Kubernetes growth and curb idle workloads | usage charge | ₹2.64 L to explain | – | Medium
Step total (approximate, lines overlap slightly) |  | up to ₹4.29 L |  | 

## Slide 9: Step 2 · Switch off, right-size and tune
Step total: up to ₹6.56 L a month
2
DAYS 30–90
Switch off what nobody uses, resize what measured load allows, and reserve and trim what stays on Azure. With Step 1 this makes the 90-day target.
What to do | Applies to | Approx. saving /mo | Proven /mo | Risk
Switch off almost-unused servers | 36 idle + 2 GPU | up to ₹2.34 L | – | Medium
Right-size servers with spare capacity | 30 servers | up to ₹53.7K | ₹21.3K | Medium
Shrink over-provisioned disks | 59 servers | up to ₹73.8K | – | Medium
Reserve and trim what stays on Azure | 45 resources | up to ₹2.95 L | – | Medium
Step total (approximate, lines overlap slightly) |  | up to ₹6.56 L |  | 

## Slide 10: Step 3 · Move Azure workloads to WebberStop
Step total: up to ₹3.34 L a month
3
DAY 60 TO MONTH 6
Quote and compliance review start in Step 1; the first workloads move from day 60. The rest follow by month 6.
What to do | Applies to | Approx. saving /mo | Proven /mo | Risk
Move Azure workloads to WebberStop | 6 workloads | up to ₹3.26 L | – | Medium
Move after compliance check | 1 workload | up to ₹7.5K | – | High
Re-platform Azure SQL and App Service first | 7 workloads | enables moves | – | Medium
Get sizes of Azure servers not in Zabbix | 7 workloads | enables moves | – | Low
Step total (approximate, lines overlap slightly) |  | up to ₹3.34 L |  | 

## Slide 11: Step 4 · Keep improving
Step total: up to ₹44.3K a month
4
ONGOING, MONTHLY CYCLE
Tune what is left, then re-run this analysis every month with fresh Zabbix data and act on what it proves.
What to do | Applies to | Approx. saving /mo | Proven /mo | Risk
Tune the remaining Azure services | 41 resources | up to ₹44.3K | – | Low
Step total (approximate, lines overlap slightly) |  | up to ₹44.3K |  | 
1 · Re-run monthly
Load fresh Zabbix and bill files each month. Every cycle re-prices the list and surfaces new idle or silent servers.
2 · Report in three buckets
Proven, confirmed by owners and assumed, shown separately against the 15–20% goal. Only the first two count as saved.
3 · Set next month's list
Owners get a short list of decisions, largest saving first, with a due date.

## Slide 12: Switch off the old Azure side of moved servers
Approx. saving: up to ₹2.01 L a month
1
STEP 1 · DAYS 0–30
Why it matters
Four servers are billed on both Azure and WebberStop. After a move the old side keeps billing until someone stops it. ProdSQL is 95% of the figure, and its Azure side still runs hot (64% CPU, disk 99.8% full).
What to do
Decide each pair in week 1, then stop (not delete) the old side for two weeks before removing it. Done by day 30.
Verify before acting
Pairs were matched by server name: confirm each is the same workload
The new side has run production for the agreed period
The old server's last backup is restorable and nothing still connects to it
₹2.01 L
a month, counting the cheaper side of each pair
Owner: Infra lead
Risk: Medium
Evidence: Owner to confirm
When: Days 0–30
Azure server | WebberStop server | Azure /mo | Webber /mo
vm-vmmargprodsql | wvm-Ecod-data3 / WVM-… | ₹5.77 L | ₹1.91 L
vmmargpaydb | VM-MARGPAY | ₹42.9K | ₹6.1K
vm-margmart-redir… | VM-MargMart-Redirect | ₹3.5K | ₹2.2K
vmmb-openapi-gate… | Wvmmb-openapi-gateway | ₹1.6K | ₹3.7K

## Slide 13: Confirm silent servers, then stop paying for them
Approx. saving: up to ₹1.26 L a month
1
STEP 1 · DAYS 0–30
Why it matters
Nine billed servers sent their last reading on 17 September and cost ₹1.26 L a month. Seven sit on 192.168.4.x addresses, so a broken monitoring link is possible and worth ruling out first.
What to do
Ask each owner in week 1: decommissioned (stop billing), moved (update the bill) or running with a broken agent (fix it). Stop billing by day 30.
Verify before acting
Is the server powered on in the WebberStop console?
If decommissioned, confirm a final backup, then stop billing
Check the monitoring link for the 192.168.4.x group first
₹1.26 L
a month if all nine are decommissioned
Owner: DevOps + app owner
Risk: Medium
Evidence: Owner to confirm
When: Days 0–30
Server (top 5 of 9) | Last reading | Saving /mo
VM-DMSSRV | 17 Sep | ₹48.1K
UAT-SERVER | 17 Sep | ₹29.0K
VM-Ewallet-SRV | 17 Sep | ₹12.2K
WIN-JENKINS-1 | 17 Sep | ₹12.1K
RE-DASH-2-LIVE | 17 Sep | ₹7.3K

## Slide 14: Ask WebberStop for the missing 40% discount
Approx. saving: up to ₹89.3K a month
1
STEP 1 · DAYS 0–30
Why it matters
Four server lines are charged at list price (₹2.23 L) because the 40% invoice discount is marked 'No'. The other 224 server lines get it. The two GPU servers are ₹84.8K of the ₹89.3K.
What to do
Write to WebberStop this week, ask whether the discount applies under the contract, and request a credit for past months. Answer by day 30.
Verify before acting
Compare the invoice lines: the discount column is 'No' for these servers
Get WebberStop's answer in writing before claiming the saving
₹89.3K
a month if the discount applies
Owner: Procurement
Risk: Low
Evidence: Owner to confirm
When: Days 0–30
Server | Line | Billed /mo | Saving /mo
VM-VoiceQA (GPU) | GPU | ₹1.33 L | ₹53.0K
VM-PDFprocess (GPU) | GPU | ₹79.4K | ₹31.8K
K8 server (unnamed) | K8 | ₹8.8K | ₹3.5K
K8 server (unnamed) | K8 | ₹2.4K | ₹962

## Slide 15: Release unused IPs and charges for retired servers
Approx. saving: up to ₹12.4K a month
1
STEP 1 · DAYS 0–30
Why it matters
Three small clean-ups on the WebberStop bill. ₹3.4K a month is proven by the bill, and ₹8.9K needs a yes from WebberStop or the Infra lead.
What to do
Release the unused public IPs in week 1. Ask WebberStop to stop backup billing for retired servers, and whether a stopped test server bills less.
Verify before acting
Each IP is not tied to a server, load balancer or firewall rule
No DNS record or customer whitelist still points at it
Backup-enabled servers on the invoice match the servers that exist
₹12.4K
a month, of which ₹3.4K is proven
Owner: DevOps, Infra lead
Risk: Low
Evidence: Bill + owner
When: Days 0–30
Item | Count | Saving /mo | Basis
Unused public IPs | 22 lines | ₹3.4K | Bill
Backups of retired servers | 7 backups | ₹4.0K | Owner
Stopped test-server billing | 1 server | up to ₹4.9K | Owner

## Slide 16: Fix servers short of CPU, memory or disk
Spend to add, not a saving
1
STEP 1 · DAYS 0–30
Why it matters
19 servers run hot: 12 have a disk 99% full or more, 2 average over 80% CPU in busy hours. The audit logged 5,627 CPU, memory and disk alerts on them in 30 days. This comes first so that resizing elsewhere never puts a stressed server at risk.
What to do
Weeks 1–2: clean logs and temp, expand the full disks. Then scale up the worst offenders. Do not shrink these.
Verify before acting
Check the alerts on each server and the last month-end
Budget for what remains: this is spend, not a saving
19 servers
short of capacity: spend to add, not a saving
Owner: DevOps + DBA
Risk: High
Evidence: Measured alerts
When: Days 0–30
Server (worst 5 of 19) | CPU p95 | Mem peak | Disk full
VMMargBooksLogDBLinux | 99% | 69% | 100%
VMMongoDBECOD | 100% | 87% | 82%
VM-eBusiness-SRV | 30% | 96% | 100%
wvm-prodsql-2 | 15% | 100% | 100%
VM-MargHR-DB | 11% | 95% | 100%

## Slide 17: Put monitoring on billed servers nobody measures
Enables savings, not a saving itself
1
STEP 1 · DAYS 0–30
Why it matters
70 billed WebberStop servers (₹9.15 L a month, about a quarter of the bill) are missing from the Zabbix audit, so nobody can say whether they are used or sized correctly. They include the new ProdSQL server and both GPU servers.
What to do
Install the Zabbix agent on the largest servers first, all 70 by day 30. After two weeks of data, each server gets a switch-off, resize or keep decision in Step 2.
Verify before acting
The agent is installed and the host registered
Re-run: each server then gets a decision
₹9.15 L
a month billed with no monitoring
Owner: DevOps
Risk: Low
Evidence: Enables savings
When: Days 0–30
Server (top 5 of 70) | Line | vCPU | Cost /mo
wvm-Ecod-data3 / WVM-Prod… | ERP | 96 | ₹1.91 L
VM-VoiceQA (GPU) | GPU | 8 | ₹1.33 L
VM-PDFprocess (GPU) | GPU | 64 | ₹79.4K
WEB-MCLOUDS-14 | CLOUD | 64 | ₹43.9K
wvm-Ecod-data / vm-e-Invo… | ERP | 8 | ₹30.4K

## Slide 18: Explain Kubernetes growth and curb idle workloads
Growth to explain: ₹2.64 L a month
1
STEP 1 · DAYS 0–30
Why it matters
The Kubernetes (CloudStack) usage charge went from ₹1.9K in June to ₹2.66 L in September, and the bill does not say which workloads drive it. It is the biggest single driver of the rise.
What to do
Ask WebberStop for the usage breakdown by namespace and node in week 1. Set limits on idle workloads. The plan targets half the growth by day 90 (₹1.32 L), which is a target, not evidence.
Verify before acting
Ask the platform team what runs in the clusters and who asked for them
Check whether the nodes are mostly idle
₹2.64 L
a month added since June, to be explained
Owner: DevOps
Risk: Medium
Evidence: Cost to explain
When: Days 0–30
Kubernetes usage charge, ₹ lakh a month
Chart: 
| Apr | May | Jun | Jul | Aug | Sep
Kubernetes (CloudStack) | 0 | 0 | 0.02 | 1.88 | 2.56 | 2.66

## Slide 19: Switch off servers that are almost unused
Approx. saving: up to ₹2.34 L a month
2
STEP 2 · DAYS 30–90
Why it matters
36 servers peaked below 15% CPU even in their busiest hours, averaged under 5% and used little memory for 30 days. They cost ₹2.34 L a month. Two GPU servers (₹2.12 L) cannot be judged: GPU load is not measured.
What to do
Owners answer by day 40. Snapshot and stop, then delete after two weeks. Off by day 75. If needed but quiet, shrink it instead.
Verify before acting
Last login and last scheduled job
Network traffic over 90 days
Keep the snapshot for the agreed retention
₹2.34 L
a month if all 36 are switched off (ceiling)
Owner: App owner + DevOps
Risk: Medium
Evidence: Owner to confirm
When: Days 30–90
Server (top 5 of 36) | Where | CPU p95 | Saving /mo
VMMargApp2NSync | Azure | 0.8% | ₹43.3K
VM-APP2N-PATCH2 | Webber | 0.6% | ₹28.4K
WEB-PREMIUM | Webber | 1.7% | ₹10.4K
wvm-pkdredis | Webber | 0.1% | ₹9.7K
wvm-Elasticsearchpkd | Webber | 0.0% | ₹8.9K

## Slide 20: Right-size servers whose load allows a smaller size
Approx. saving: up to ₹53.7K a month
2
STEP 2 · DAYS 30–90
Why it matters
12 servers can run on half their vCPUs: busy-hour CPU is under 35% and spikes stay within the smaller size. That saves ₹21.3K, proven by measured load and prices already on the bill. 13 more need a price or DBA check (up to ₹32.4K).
What to do
Start in week 5 with the 12 proven; one server per maintenance window, standby first. Also cap SQL Server memory on 5 database servers: no saving, but it stops false memory alarms.
Verify before acting
Month-end peaks fall inside the 30-day window
Licences that count by core (Windows, SQL) allow it
DBA checks waits and IO latency for any database
₹53.7K
a month: ₹21.3K proven, ₹32.4K to confirm
Owner: DevOps; DBA for databases
Risk: Medium
Evidence: Proven by load
When: Days 30–90
Server (top 5 of 12) | vCPU | CPU p95 | Saving /mo
wvm-pkdapi | 16 → 8 | 20% | ₹4.1K
Wvmmb1-salepurchasema… | 4 → 2 | 14% | ₹3.0K
Wvmmb1-salepurchasema… | 4 → 2 | 16% | ₹3.0K
Wvmmb1-salepurchasema… | 4 → 2 | 12% | ₹3.0K
Wvmmb1-ledger-1 | 4 → 2 | 6% | ₹1.7K

## Slide 21: Shrink over-provisioned disks
Approx. saving: up to ₹73.8K a month
2
STEP 2 · DAYS 30–90
Why it matters
59 servers have volumes of 100 GB or more that never passed 50% full in 30 days. About 19,919 GB can be reclaimed, priced at the bill's own storage rate (about ₹3.3 per GB a month).
What to do
Disks cannot shrink in place: create a smaller volume, copy, swap. Start with the 10 largest data disks (not C: or /) in week 6.
Verify before acting
What fills the disk: data, logs, backups or temp
The growth trend is flat or slow
A new smaller disk is planned and the data copied
₹73.8K
a month, an estimate from the bill's storage rate
Owner: DevOps
Risk: Medium
Evidence: Owner to confirm
When: Days 30–90
Server (top 5 of 59) | Disk GB | Used GB | Saving /mo
wvm-mbsql-4 | 2,998 | 670 | ₹6.5K
wvm-mbsql-8 | 4,050 | 1,855 | ₹3.6K
WIN-Beta-Srv | 1,199 | 33 | ₹3.6K
WEB-PREMIUM | 1,199 | 33 | ₹3.6K
wvm-mbsql-12 | 1,800 | 635 | ₹3.3K

## Slide 22: Reserve and trim what stays on Azure and in backup
Approx. saving: up to ₹2.95 L a month
2
STEP 2 · DAYS 30–90
Why it matters
These are the large Azure and backup lines that will stay. The percentages (10–25%) are assumptions, so ₹2.95 L is an estimate, not a saving, until owners review the biggest resources. Reservations leave out Azure servers that retire or move, which cuts that line to ₹67.7K.
What to do
Trim snapshots, storage accounts and disks in weeks 5–8. Buy reservations only for servers that stay, once the move list is firm (day 60). Review backup retention.
Verify before acting
Decide which Azure servers stay before committing
Agree a retention period per workload
Check reservations on servers being retired
₹2.95 L
a month estimate at assumed 10–25% per line
Owner: Cloud lead + Infra lead
Risk: Medium
Evidence: Estimate
When: Days 30–90
Line | Cost /mo | Assumed | At stake
Azure managed disks | ₹6.05 L | 15% | ₹90.8K
Azure VM reservations | ₹2.71 L | 25% | ₹67.7K
Azure storage accounts | ₹2.50 L | 15% | ₹37.5K
Azure snapshots | ₹1.88 L | 20% | ₹37.5K
Backup storage | ₹3.45 L | 10% | ₹34.5K
App Service plans | ₹1.79 L | 15% | ₹26.9K

## Slide 23: Move Azure workloads to WebberStop
Approx. saving: up to ₹3.26 L a month
3
STEP 3 · DAY 60 TO MONTH 6
Why it matters
Six Azure workloads cost ₹4.61 L a month for servers, disks and network items. The same sizes at WebberStop's current prices are about ₹1.35 L. Azure data-transfer and licence differences are not counted, so the real saving is likely higher.
What to do
Quote and compliance review in days 0–30. Pilot the first workload by day 60, and land the first three (₹2.52 L) by day 90. The other three follow by month 6.
Verify before acting
Legal and security confirm the data may sit with WebberStop
Windows and SQL Server licence terms allow the move
The pilot measures latency to users and to databases
₹3.26 L
a month, an estimate (Azure ₹4.6 L → ₹1.3 L)
Owner: Cloud lead + app owners
Risk: Medium
Evidence: Estimate
When: Day 60 to month 6
Workload | Azure /mo | Saving /mo | Lands by
VM-App2 | ₹1.73 L | ₹1.49 L | Day 90
VM-ReportServer | ₹1.13 L | ₹57.6K | Day 90
VM-APP2-New | ₹60.6K | ₹38.6K | Month 6
VM-APP2NSYNC | ₹52.6K | ₹45.5K | Day 90
ECOD | ₹46.6K | ₹27.3K | Month 6
WhatsApp | ₹14.3K | ₹7.7K | Month 6
Notes: WebberStop estimate = RAM and disk of each server from Zabbix, vCPU assumed as RAM divided by 4, priced at the rates WebberStop charges on the current bill. Excludes Azure data-transfer and licence differences.

## Slide 24: Before more workloads can move
3
STEP 3 · DAY 60 TO MONTH 6
COMPLIANCE FIRST
₹7.5K
a month at stake · 1 workload
ABHA (health data) looks cheaper at WebberStop, but only if Legal and Security approve data location, certifications and customer contracts. Start the review in week 1.
Owner: Legal + Security · Risk: High
RE-PLATFORM FIRST
₹1.84 L
a month on Azure SQL, App Service · 7 workloads
These services cannot be copied to WebberStop as they are. They must be rebuilt as servers with SQL licences first. The largest is MargBooks-VM (₹1.27 L). Get a quote in Step 1.
Owner: App owners + DBA · Risk: Medium
SERVER SIZES FIRST
₹7.18 L
a month on Azure · 7 workloads
These servers are not in Zabbix, so their size is unknown and they cannot be priced. The largest is VM-MargME9 (₹2.98 L). Install the agent or list the sizes in Step 1.
Owner: DevOps · Risk: Low

## Slide 25: Tune the rest, and re-run the analysis monthly
Approx. saving: up to ₹44.3K a month
4
STEP 4 · ONGOING
Why it matters
After the big moves, the remaining Azure services add up to ₹44.3K a month at an assumed 15%. More valuable is the cycle: every month, new Zabbix data decides the next switch-off, resize or move.
What to do
Review the remaining services as owners free up. Re-run this analysis monthly, report proven, confirmed and assumed savings separately, and set the next month's list.
Verify before acting
Each line reviewed by the owner of the service
Monthly report shows proven, confirmed and assumed separately
New silent or idle servers are caught each cycle
₹44.3K
a month estimate, plus the monthly cycle
Owner: Cloud lead + Infra lead
Risk: Low
Evidence: Estimate
When: From day 90
Service (top 6) | At stake /mo
Azure SQL | ₹18.3K
Azure NAT gateways | ₹8.5K
Azure application gateways | ₹7.3K
Azure Log Analytics | ₹3.9K
Azure public IPs | ₹3.2K
Azure VPN gateways | ₹1.7K

## Slide 26: Who confirms what, and by when
Owner | Confirms | By when
Infra lead | Old Azure side of 4 servers (₹2.01 L); backups of retired servers; backup retention | Day 30; retention day 90
Procurement | Missing 40% discount (₹89.3K); whether stopped test servers bill less; WebberStop quote for moves | Day 30; quote day 30
DevOps, with app owners | Silent servers (₹1.26 L), IPs, capacity fixes, monitoring, Kubernetes breakdown; then idle (₹2.34 L), right-sizing, disks | Day 30; Step 2 by day 90
DBA | SQL memory cap, database right-sizing, hot database servers, re-platforming (with app owners) | Days 30–90; re-platform by month 6
Cloud lead, with app owners | Reservations, trims, first 3 moves (₹2.52 L estimate), then remaining moves and tuning | Day 90; month 6; monthly
Legal + Security | Data-location and contract sign-off before any workload moves (ABHA first) | Review starts week 1; clear by day 45
Owners are the roles named in the plan. Days count from approval of this plan.

## Slide 27: What we need from management this week
1
Mandate the owners to answer within 14 days
Step 1 and 2 owners confirm or reject each action. Proven today: ₹24.8K; up to ₹7.7 L more depends on their answers.
2
Authorise two requests to WebberStop
The missing 40% discount, and a quote for the six workloads that could move (₹3.26 L estimate), with the first three by day 90.
3
Start the legal and security review now
Data location and customer contracts, before any workload moves. ABHA is the first flagged as regulated.
4
Set aside budget for capacity fixes
19 servers are short of CPU, memory or disk. DevOps and DBA to size the amount in week 1.
5
Review progress at day 30 and day 90
Report proven, confirmed and assumed savings separately against the 15–20% goal (₹10.2 L to ₹13.6 L a month).